## Sheet1
Task | Priority | Team | # of People on Task | Status | Start date | Expected Finish | Actual Finish | Milestone | Notes
Skeleton Code | P1 | Game Logic | 5 | Completed | 2024-10-28 | 2024-10-31 | 2024-11-01 | Iteration 1 | basic skeleton code structure for diagram preparation
Skeleton Code | P1 | Leaderboard & Matchmaking | 6 | Completed | 2024-10-28 | 2024-10-31 | 2024-11-01 | Iteration 1 | basic skeleton code structure for diagram preparation
Skeleton Code | P1 | GUI | 5 | Completed | 2024-10-28 | 2024-10-31 | 2024-11-04 | Iteration 1 | basic skeleton code structure for diagram preparation
Skeleton Code | P1 | Networking | 2 | Completed | 2024-10-28 | 2024-10-31 | 2024-11-01 | Iteration 1 | basic skeleton code structure for diagram preparation
Skeleton Code | P1 | Authentication & Profile | 5 | Completed | 2024-10-28 | 2024-10-31 | 2024-11-01 | Iteration 1 | basic skeleton code structure for diagram preparation
Tic Tac Toe Functionality | P1 | Game Logic | 2 | In progress | 2024-11-01 | 2024-11-10 | N/A | Iteration 2 | implement functional tictactoe game on console
Checkers Functionality | P1 | Game Logic | 2 | In progress | 2024-11-01 | 2024-11-10 | N/A | Iteration 2 | implement functional checkers game on console
Connect4 Funtionality | P1 | Game Logic | 2 | In progress | 2024-11-01 | 2024-11-10 | N/A | Iteration 2 | implement functional connect4 game on console
GUI Pages / Basic Functionality | P1 | GUI | 6 | In progress | 2024-11-04 | 2024-11-16 | N/A | Iteration 2 | implement all pages and basic setup for integration preparation
Profile Integration | P2 | Authentication & Profile | 4 | Not started | 2024-11-17 | 2024-11-20 | N/A | Iteration 3 | integrate profile and authentication system into program
Leaderboard Integration | P2 | Leaderboard & Matchmaking | 4 | Not started | 2024-11-17 | 2024-11-20 | N/A | Iteration 3 | integrate leaderboard system into program
Network Integration | P2 | Networking | 3 | Not started | 2024-11-19 | 2024-11-23 | N/A | Iteration 3 | Integrate Network functions that imitate the functionality of network into system
Game Integration | P2 | Game Logic | 5 | Not started | 2024-11-17 | 2024-11-20 | N/A | Iteration 3 | integrate game functions into GUI with function player interactions
Database Integration | P2 | Integration | 2 | Not started | 2024-11-26 | 2024-11-30 | N/A | Iteration 3 | creation of data and display of data into system
Junit Testing | P3 | Team Leaders | 10 | Not started | 2024-11-28 | 2024-12-01 | N/A | Iteration 3 | create junit tests to test all class functionality to rule out errors
Final Iteration of Code | P3 | Everyone | 25 | Not started | 2024-12-01 | 2024-12-03 | N/A | Iteration 3 | All code and final refinements done and ready to present